## A3
Closing the win-rate gap in outbound-sourced mid-market deals
Jordan Ellis, Sales Manager · 2026-02-23 · Team: Priya Anand, RevOps, Sam Cole, Sales Enablement · Sponsor: Renee Okafor, VP Sales
BACKGROUND
Outbound-sourced mid-market deals have carried the team's forecast for two years at a stable ~28% win rate. The last QBR flagged three straight quarters of decline, and pipeline coverage is starting to compensate for a falling win rate rather than genuine growth — that's a trend that erodes the whole forecast if it isn't reversed before next quarter's planning.
PROBLEM STATEMENT
Win rate on outbound-sourced mid-market deals has fallen from a 28% standard to a nine-week average of 21%, against a 32% target.
TARGET · ACTUAL · GAP · STANDARD
Target | Actual | Gap | Standard
32% | 21% | 11% | 28%
[6 empty] | Date | Actual | Target | Standard
[6 empty] | 2025-11-03 | 27 | 32 | 28
[6 empty] | 2025-11-17 | 25 | 32 | 28
[6 empty] | 2025-12-01 | 24 | 32 | 28
[6 empty] | 2025-12-15 | 22 | 32 | 28
[6 empty] | 2025-12-29 | 21 | 32 | 28
[6 empty] | 2026-01-12 | 22 | 32 | 28
[6 empty] | 2026-01-26 | 20 | 32 | 28
[6 empty] | 2026-02-09 | 21 | 32 | 28
ROOT CAUSE — PARETO (ranked by impact)
[6 empty] | Category | Value | Cumulative %
[6 empty] | No decision / stalled | 420 | 53.8
[6 empty] | Lost to competitor | 180 | 76.9
[6 empty] | Price objection | 95 | 89.1
[6 empty] | Budget cut post-approval | 60 | 96.8
[6 empty] | Other / one-off | 25 | 100
NO DECISION / STALLED — BREAKDOWN
Single point of contact, no second stakeholder identified: 310
Champion changed roles or left mid-cycle: 70
Business case never quantified: 40
5-WHYS
Why 1: Lost pipeline value is dominated by deals that went dark with no decision — not losses to a competitor — and within that, three-quarters of the value traces to deals that only ever had a single point of contact.
Why 2: Reps aren't identifying a second stakeholder early: the first responsive contact gets treated as sufficient to advance the deal, whether or not they can actually build internal consensus.
Why 3: There's no discovery-stage requirement to name an economic buyer or additional stakeholder before a deal moves to a demo — nothing stops a deal advancing on one contact's interest alone.
Why 4: The qualification checklist was built for the inbound motion, where the requester is often the buyer, and was never updated when outbound became a majority of mid-market pipeline — reps are following a checklist that assumes a buyer profile most of their current deals don't match.
Root cause: The discovery-stage qualification checklist still assumes the inbound buyer profile and never added a multi-threading requirement for outbound deals, so reps advance on a single contact's interest and the deal stalls once that person can't get internal buy-in alone.
COUNTERMEASURES
Description |  | Linked cause | Owner | Due | Expected effect
Add a mandatory 'second stakeholder identified' gate in the CRM before a deal can move from Discovery to Demo — a named economic buyer or budget holder has to be logged, not just the rep's confidence that one exists. |  | The qualification checklist never added a multi-threading requirement for outbound deals. | Priya Anand | 2026-03-09 | Stops single-contact deals from silently advancing — the gap surfaces at Discovery, while there's still time to multi-thread, instead of three months later at 'no decision.'
Build a short multi-threading discovery script — specific questions that surface a second stakeholder in the first two calls, not left to individual rep judgement. |  | Reps aren't identifying a second stakeholder early because nothing requires it or shows them how. | Sam Cole | 2026-03-09 | Gives reps a repeatable way to hit the new stage gate rather than leaving it as an unfunded mandate.
EFFECT CONFIRMATION
Track two numbers weekly for 8 weeks: the win rate against the 32% target, and the percentage of active outbound deals with a second stakeholder logged by Discovery exit. Expect the stakeholder-identified rate to move first — it's a leading indicator — with win rate following within one full sales cycle (~6-8 weeks for this segment).
FOLLOW-UP ACTIONS
Action |  |  | Owner | Due | Status
Update the CRM stage-gate criteria and qualification checklist documentation. |  |  | Priya Anand | 2026-03-13 | not-started
Train all outbound reps on the multi-threading discovery script. |  |  | Sam Cole | 2026-03-20 | not-started
Review results after one full quarter; if the win rate recovers, extend the same Discovery-stage gate to the enterprise segment. |  |  | Jordan Ellis | 2026-06-01 | not-started