## Cascade map
Northwind Fabrication — FY2027 cascade map
Parent plan: Northwind Fabrication — FY2027 Hoshin Kanri · Oksana Petrova, Plant Manager · 2027-01-26 · Team: Priya Nair, Ops Manager · Sponsor: Board of Directors
SUMMARY
Parent objectives | Cascaded | Cascade coverage | Dark objectives | Units
3 | 2 | 66.7% | 1 | 3
Dark objectives — no unit has committed to these at all: Cut the late-shipment rate from 14% to 6%
PARENT OBJECTIVES
Objective | Target
Reduce average order lead time to 12 days | 12-day average by Q4 FY2027
Cut the late-shipment rate from 14% to 6% | 6% late-shipment rate by Q4 FY2027
Launch a repeat-customer priority queue | Live by Q2 FY2027; 20% of repeat orders routed through it by Q4
UNIT LOAD
Unit | Objectives owned
CNC Shop Floor | 1
Scheduling Team | 1
Quality Team | 0
CASCADE LINKS
Unit | Local objective | Owner | Status
CNC Shop Floor | Complete second-shift hiring and training, and hit a 12-day average lead time on CNC-routed orders by Q4 | Marcus Webb, Shop Supervisor | committed
Scheduling Team | Build and launch the repeat-customer priority queue in the scheduling system by Q2, with 20% of repeat orders routed through it by Q4 | Dana Ruiz, Scheduling Lead | committed
Quality Team | Cut the late-shipment rate to 6% — proposed at the Q1 cascade review, owner not yet named | TBD | proposed
NARRATIVE
Two of the plan's three annual objectives have a real, committed owner at the team level: the CNC Shop Floor has taken on the lead-time objective, and Scheduling has taken on the priority-queue launch. The late-shipment objective is still only proposed to Quality — raised at the Q1 cascade review, but nobody has actually agreed to own it yet. Cascade coverage sits at 66.7% on that basis, not 100%, because a proposal isn't the same thing as a commitment.
NEXT STEPS
Description |  | Linked finding | Impact | Effort | Owner | Due
Get a named owner and a committed local objective from Quality for the late-shipment target before the Q2 business review. |  | Cut the late-shipment rate from 14% to 6% — proposed to Quality, not yet committed | high | low | Oksana Petrova — 2027-02-15
Confirm the CNC Shop Floor's second-shift hiring is actually on track to support the 12-day target, not just committed on paper. |  | CNC Shop Floor — committed to the lead-time objective | medium | low | Priya Nair — 2027-02-28