## First-pass yield
Bracket assembly line — first-pass yield
Dana Whitfield, Line Supervisor · 2026-02-10 · Team: Marcus Lee, Quality, Priya Nair, Production · Sponsor: Alex Romero, Plant Manager
SCOPE
Scope runs from raw component prep through final inspection for the model-B bracket assembly line only. Excludes packaging and shipping, which are a separate value stream with their own defect log.
STAGES
Stage | Entered | Advanced | Conversion %
Component prep | 500 | 480 | 96.00%
Sub-assembly | 480 | 450 | 93.75%
Final assembly | 450 | 430 | 95.56%
Inspection | 430 | 410 | 95.35%
ROLLED YIELD
82.00%
480/500 × 450/480 × 430/450 × 410/430 × 100 = 82.00%
Weakest stage: Sub-assembly (93.75% conversion, 30 units lost)
NARRATIVE
Sub-assembly is the weakest stage at 93.75% conversion, losing 30 of 480 units — the single largest loss of any stage in absolute terms. Operator notes point to fixture drift as the likely cause, not a one-off quality issue, which suggests a calibration schedule would address the root cause rather than just catching more defects downstream. Rolled yield across all four stages is 82.00%, meaning roughly one in six units started is lost somewhere before inspection.
COUNTERMEASURES
Description |  | Linked finding | Impact | Effort | Owner | Due
Add a mid-shift fixture recalibration check at sub-assembly, logged on the station's standard work sheet. |  | Sub-assembly — weakest stage at 93.75% conversion, 30 units lost | high | low | Priya Nair — 2026-02-24
Set a rolled-yield target of 90% and re-run this tracker after the recalibration schedule has been in place for a full month to confirm it actually moved the number, not just sub-assembly's local rate. |  | Rolled yield — 82.00% overall, below the 90% standard for this line | medium | low | Marcus Lee — 2026-03-24