## FMEA
FMEA — Line 2 paint booth changeover procedure
The new Line 2 paint booth changeover procedure, ahead of its kaizen-event rollout · Priya Nair, Line Supervisor · 2026-02-24 · Team: Marcus Webb, Paint Booth Lead, Dana Ruiz, Scheduling · Sponsor: Oksana Petrova, Plant Manager
Top risks (vital few, by RPN): Nozzle cleaning step
ITEMS — RANKED BY RISK PRIORITY NUMBER (RPN)
Item | Failure mode | Effect | S | Cause | O | Controls | D
Nozzle cleaning step RPN 280 | Cleaning cycle cut short under time pressure to hit the new 25-minute target | Color contamination carries into the next batch, caught only at final inspection | 8 | New target time creates pressure to skip the full cleaning cycle | 5 | Visual check by the operator only — no independent verification | 7
→ Recommended action: Add a timer-gated cleaning step the changeover can't proceed past until the full cycle completes (Marcus Webb — 2026-02-27)
Color mixing during changeover RPN 168 | Wrong paint color mixed during a changeover | Full batch scrapped; changeover time doubles while the error is caught and corrected | 7 | Operator mixes from memory instead of the written recipe card | 4 | None yet — the new procedure doesn't specify a recipe-card check step | 6
→ Recommended action: Add a mandatory recipe-card check as the first step of every changeover, signed off before mixing starts (Marcus Webb — 2026-02-27)
Queue board update RPN 120 | Board isn't updated in real time as small-batch orders arrive | Scheduler reverts to case-by-case judgement calls, defeating the sequencing rule the A3 put in place | 5 | No one is explicitly assigned to own keeping the board current | 6 | None — ownership wasn't assigned in the event | 4
→ Recommended action: Name the scheduler as the board's explicit owner, with a start-of-shift check as part of their standard work (Dana Ruiz — 2026-03-02)
Fixture reuse across colors RPN 90 | A reused fixture carries residue from the previous color | Surface defect on the finished part | 6 | The new changeover procedure doesn't specify fixture-swap timing | 3 | Operator judgement only | 5
→ Recommended action: Add a fixture-swap checkpoint to the procedure, tied to color family rather than left to judgement (Marcus Webb — 2026-03-06)
Narrative
Severity first: no failure mode here scores 9 or 10 (nothing that could hurt someone or break a legal requirement), so nothing needs action on severity alone and the rest can be ranked by risk priority number. The nozzle cleaning step is the single vital-few risk here, at a risk priority number well clear of everything else on the list — the new 25-minute target creates real pressure to shorten a cleaning cycle that has no independent check behind it, and a missed contamination event wouldn't be caught until final inspection. The color-mixing risk sits second, sharing the same root pattern (the redesigned procedure moved faster without adding the verification steps the old, slower procedure implicitly had time for), but it's the nozzle cleaning step that should get the recommended action actually built and verified first.