## Objectives & Catchball
Northwind Fabrication — FY2027 Hoshin Kanri
Oksana Petrova, Plant Manager · 2027-01-12 · Team: Priya Nair, Ops Manager, Dana Ruiz, Scheduling Lead, Marcus Webb, Shop Supervisor · Sponsor: Board of Directors
TRUE NORTH
Northwind Fabrication becomes the shop customers call first for time-sensitive custom orders — the fastest, most reliable option in the region.
LONG-TERM BREAKTHROUGH OBJECTIVES
Statement | Target
Cut average order lead time from 18 days to 7 days | 7-day average lead time by FY2029
Grow repeat-customer revenue share from 40% to 65% | 65% repeat revenue by FY2029
ANNUAL OBJECTIVES
Statement | Target
Reduce average order lead time to 12 days | 12-day average by Q4 FY2027
Cut the late-shipment rate from 14% to 6% | 6% late-shipment rate by Q4 FY2027
Launch a repeat-customer priority queue | Live by Q2 FY2027; 20% of repeat orders routed through it by Q4
STRATEGIES
Statement | Owner
Add a second CNC shift to relieve the fabrication bottleneck | Priya Nair, Ops Manager
Build and launch a repeat-customer priority queue in the scheduling system | Dana Ruiz, Scheduling Lead
Standardize the changeover procedure between small-batch and custom orders | Marcus Webb, Shop Supervisor
METRICS
Statement | Target
Average order lead time (days) | 12 days by Q4
Late-shipment rate (%) | 6% by Q4
Repeat orders routed through priority queue (%) | 20% by Q4
CATCHBALL
Re: Reduce average order lead time to 12 days
Ops leadership proposed: Cut average lead time to 10 days this year.
Shop floor supervisors responded: 10 days isn't achievable without a second CNC operator, and hiring won't clear background/training until Q2 at the earliest. 12 days is realistic with the schedule change alone.
Agreed: Annual objective set at 12 days. A second-shift hire is queued as a strategy contingent on Q2 lead-time data.
Re: Cut the late-shipment rate from 14% to 6%
Quality lead proposed: Target a 4% late-shipment rate.
Scheduling responded: 4% assumes the priority queue is already live, which won't happen until Q2. 6% is achievable across the full year given that timing.
Agreed: Target set at 6%, reviewed at the Q2 business review once the priority queue is live.

## X-Matrix
Northwind Fabrication — FY2027 Hoshin Kanri
Oksana Petrova, Plant Manager · 2027-01-12 · Team: Priya Nair, Ops Manager, Dana Ruiz, Scheduling Lead, Marcus Webb, Shop Supervisor · Sponsor: Board of Directors
◎ |  | Reduce average order lead time to 12 days Target: 12-day average by Q4 FY2027 | ◎
○ |  | Cut the late-shipment rate from 14% to 6% Target: 6% late-shipment rate by Q4 FY2027 | ○ | ◎
△ | ◎ | Launch a repeat-customer priority queue Target: Live by Q2 FY2027; 20% of repeat orders routed through it by Q4 |  |  | ◎
Cut average order lead time from 18 days to 7 days Target: 7-day average lead time by FY2029 | Grow repeat-customer revenue share from 40% to 65% Target: 65% repeat revenue by FY2029 | TRUE NORTH Northwind Fabrication becomes the shop customers call first for time-sensitive custom orders — the fastest, most reliable option in the region. | Average order lead time (days) Target: 12 days by Q4 | Late-shipment rate (%) Target: 6% by Q4 | Repeat orders routed through priority queue (%) Target: 20% by Q4
◎ |  | Add a second CNC shift to relieve the fabrication bottleneck Owner: Priya Nair, Ops Manager | ◎ | ○
△ | ◎ | Build and launch a repeat-customer priority queue in the scheduling system Owner: Dana Ruiz, Scheduling Lead |  |  | ◎
○ |  | Standardize the changeover procedure between small-batch and custom orders Owner: Marcus Webb, Shop Supervisor | ○ | ◎
◎ Primary ○ Secondary △ Weak
Blank cell — no relationship claimed. Left: long-term objectives · Top: annual objectives · Right: metrics · Bottom: strategies.