## Objectives & Catchball
Beacon Analytics — FY2027 Revenue Hoshin Kanri
Renee Okafor, VP Sales · 2027-01-08 · Team: Jordan Ellis, Sales Manager, Priya Anand, RevOps, Sam Cole, Sales Enablement · Sponsor: Board of Directors
TRUE NORTH
Beacon Analytics becomes the platform mid-market RevOps teams standardize on and expand within — not just adopt and quietly leave alone.
LONG-TERM BREAKTHROUGH OBJECTIVES
Statement | Target
Grow net revenue retention from 98% to 115% | 115% NRR by FY2029
Establish outbound as a repeatable, profitable growth channel rather than inbound-dependent growth | 40% of new ARR from outbound by FY2029
ANNUAL OBJECTIVES
Statement | Target
Close the outbound win-rate gap identified in Q1's deal A3 | 30% win rate by Q4 FY2027
Cut proposal-stage wait time in half, per the funnel value stream map's finding | 3.5-day average by Q4 FY2027
Launch a systematic expansion motion for accounts past 90 days | 10% of 90+ day accounts in an active expansion play by Q4
STRATEGIES
Statement | Owner
Roll out the deal A3's Discovery-stage multi-threading gate and the funnel VSM's pricing pre-approval tiers | Priya Anand, RevOps
Cap WIP between demo and proposal with pull-based scheduling, per the funnel VSM's second countermeasure | Jordan Ellis, Sales Manager
Build a customer-success-led expansion playbook for accounts past 90 days | Renee Okafor, VP Sales
METRICS
Statement | Target
Outbound win rate (%) | 30% by Q4
Proposal-stage wait time (days) | 3.5 days by Q4
90+ day accounts in an active expansion play (%) | 10% by Q4
CATCHBALL
Re: Close the outbound win-rate gap identified in Q1's deal A3
Sales leadership proposed: Target a 35% win rate this year.
Frontline reps and RevOps responded: 35% assumes the deal A3's multi-threading gate and pricing pre-approval tiers are live and adopted for a full two quarters — rollout doesn't finish until end of Q1, leaving three quarters of real effect, not four. 30% is realistic in that window.
Agreed: Annual objective set at 30%, reviewed at the Q3 business review with 35% as the stretch case if Q2 tracking is ahead of pace.
Re: Cut proposal-stage wait time in half, per the funnel value stream map's finding
RevOps proposed: Cut proposal-stage wait to 2 days.
Deal desk and legal responded: 2 days isn't realistic without a second pricing approver, which isn't budgeted this year. 3.5 days is achievable from pre-approved standard tiers alone, per the funnel VSM's countermeasure.
Agreed: Target set at 3.5 days; a second approver becomes an FY2028 strategy candidate if 3.5 days still isn't enough once the tiers are live.

## X-Matrix
Beacon Analytics — FY2027 Revenue Hoshin Kanri
Renee Okafor, VP Sales · 2027-01-08 · Team: Jordan Ellis, Sales Manager, Priya Anand, RevOps, Sam Cole, Sales Enablement · Sponsor: Board of Directors
△ | ◎ | Close the outbound win-rate gap identified in Q1's deal A3 Target: 30% win rate by Q4 FY2027 | ◎ | ○
| ○ | Cut proposal-stage wait time in half, per the funnel value stream map's finding Target: 3.5-day average by Q4 FY2027 |  | ◎
◎ |  | Launch a systematic expansion motion for accounts past 90 days Target: 10% of 90+ day accounts in an active expansion play by Q4 |  |  | ◎
Grow net revenue retention from 98% to 115% Target: 115% NRR by FY2029 | Establish outbound as a repeatable, profitable growth channel rather than inbound-dependent growth Target: 40% of new ARR from outbound by FY2029 | TRUE NORTH Beacon Analytics becomes the platform mid-market RevOps teams standardize on and expand within — not just adopt and quietly leave alone. | Outbound win rate (%) Target: 30% by Q4 | Proposal-stage wait time (days) Target: 3.5 days by Q4 | 90+ day accounts in an active expansion play (%) Target: 10% by Q4
△ | ◎ | Roll out the deal A3's Discovery-stage multi-threading gate and the funnel VSM's pricing pre-approval tiers Owner: Priya Anand, RevOps | ◎ | ○
| ○ | Cap WIP between demo and proposal with pull-based scheduling, per the funnel VSM's second countermeasure Owner: Jordan Ellis, Sales Manager |  | ◎
◎ |  | Build a customer-success-led expansion playbook for accounts past 90 days Owner: Renee Okafor, VP Sales |  |  | ◎
◎ Primary ○ Secondary △ Weak
Blank cell — no relationship claimed. Left: long-term objectives · Top: annual objectives · Right: metrics · Bottom: strategies.