## Implementation plan
Andon escalation rollout — Fabrication Cell 3
Fabrication Cell 3 — andon escalation rollout · Dana Ruiz, Cell Lead · 2026-04-10 · Team: Raj Patel, Controls Engineer · Sponsor: Marcus Lee, Quality Manager
SUMMARY
Target completion | Done | Overdue | Unowned | Us / Them / Joint
2026-05-01 (21 days) | 0 / 5 | 1 | 1 | 2 / 2 / 1
SUMMARY NOTE
Roll out the new andon call-button escalation rule (two unresolved calls in 15 minutes pages the shift supervisor directly) across all three shifts on Fabrication Cell 3, following the kaizen event that designed it.
MILESTONES
Description |  | Owner party | Owner | Target date | Status
Update the andon call-button escalation logic in the Cell 3 PLC |  | them | Raj Patel, Controls Engineer | 2026-04-05 | in-progress
Train first-shift operators on the new escalation flow |  | us | Dana Ruiz, Cell Lead | 2026-04-15 | not-started
Train second-shift operators on the new escalation flow |  | them | Unassigned | 2026-04-20 | not-started
Confirm andon response-time logging captures the new escalation tiers |  | joint | Dana Ruiz & Raj Patel | 2026-04-25 | not-started
Go live across all three shifts |  | us | Dana Ruiz, Cell Lead | 2026-05-01 | not-started
RISKS
• The PLC logic change depends on Controls' quarterly change-freeze schedule — if it slips past the freeze window, the whole rollout slips a full quarter.
• Second shift's supervisor turnover last month means there may be nobody who actually owns that shift's training yet — exactly what the unowned milestone above is flagging.
NARRATIVE
One of five milestones — the PLC escalation-logic update — is already overdue relative to today's date, and second-shift training has no named owner yet. The plan is genuinely cross-functional, not something the improvement team could execute alone: two milestones belong to the cell lead, two to outside teams (Controls and second shift), and one is joint. 21 days remain to the May 1 go-live.