## Implementation plan
Northline Freight — mutual action plan to close
Northline Freight · Jordan Ellis, Sales Manager · 2027-03-05 · Team: Priya Anand, RevOps · Sponsor: Renee Okafor, VP Sales
SUMMARY
Target completion | Done | Overdue | Unowned | Us / Them / Joint
2027-03-31 (26 days) | 0 / 6 | 1 | 1 | 2 / 2 / 2
SUMMARY NOTE
Sequences Northline Freight's path from an approved business case to a signed contract, following directly from Northline's own business case for Beacon Analytics.
MILESTONES
Description |  | Owner party | Owner | Target date | Status
Beacon Analytics: deliver completed security review documentation |  | us | Priya Anand, RevOps | 2027-02-28 | in-progress
Northline: get CFO budget sign-off |  | them | Unassigned | 2027-03-14 | not-started
Joint technical validation call — data migration walkthrough |  | joint | Jordan Ellis & Northline's VP RevOps | 2027-03-10 | not-started
Northline: circulate the business case internally to finance |  | them | Northline's VP RevOps | 2027-03-07 | not-started
Beacon Analytics: send final contract redline |  | us | Jordan Ellis, Sales Manager | 2027-03-20 | not-started
Signed contract |  | joint | Jordan Ellis & Northline's VP RevOps | 2027-03-31 | not-started
RISKS
• Northline's CFO sign-off has no named owner yet on their side — if it stays unassigned past their mid-March board cycle, budget approval could slip to next quarter entirely.
• The security review documentation is already a week behind — if it slips further, it becomes the pacing item for both the technical validation call and the final contract redline.
NARRATIVE
One of six milestones — the security review documentation — is already overdue, and the CFO sign-off milestone has no named owner on Northline's side yet, which is worth flagging directly rather than assuming it will happen. This genuinely functions as a mutual plan, not a one-sided ask: two milestones belong to Beacon Analytics, two to Northline, and two are joint. 26 days remain to the March 31 target close.