## Kaizen charter
Reduce onboarding support ticket resolution time
Sponsor: Alex Romero, VP Product · Facilitator: Priya Nair, Customer Success · 2026-09-14 to 2026-09-18
OPPORTUNITY
Support ticket volume spikes in the first two weeks after signup, and resolution time for these tickets runs well above the team's overall average. Customer interviews point to unclear setup steps, not product defects, as the likely driver — this hasn't been tested against a week of focused, cross-functional attention yet.
OBJECTIVE
Cut median resolution time for first-two-weeks onboarding tickets (tagged 'setup' or 'SSO') from 6.2 hours to under 3 hours by the end of the event week, without increasing the reopened-ticket rate.
SCOPE — IN
Onboarding tickets tagged 'setup' or 'SSO' opened within the first 14 days of a new account. This week covers the triage process, the top 3 setup docs, and the initial-response macro library.
SCOPE — OUT
Product code changes, pricing or contract questions, and tickets from accounts older than 14 days.
ROSTER & RACI — 1 accountable
Name | Role | RACI
Priya Nair | Facilitator | R
Alex Romero | Sponsor | A
Marcus Lee | Support lead | R
Dana Whitfield | Product | C
Support team | Frontline agents | I
READINESS — 4 of 6 ready (67%)
Item | Ready | Note
Two weeks of ticket data pulled and tagged by setup/SSO category | Y
Top 3 setup docs identified with current view/bounce data | Y
Baseline median resolution time confirmed (6.2 hours) | Y
Sponsor briefed on objective and event dates | Y
Support team notified of event week and coverage plan | N
Workspace booked for daily standups | N
NARRATIVE
Four of six readiness items are confirmed — ticket data is pulled and tagged, the top docs are identified, the baseline is captured, and the sponsor is briefed. Two are still open: the support team hasn't been notified of the event week yet, and no workspace is booked for daily standups. Both are quick to close before the event starts. The roster has exactly one accountable owner, with Priya and Marcus responsible for running the event day to day.