## Kaizen charter
Beacon Analytics — marketing operating system charter
Sponsor: Renee Okafor, VP Sales · Facilitator: Priya Anand, RevOps · 2027-01-18 to 2027-02-01
OPPORTUNITY
The FY2027 marketing true north statement found that one of its four pillars -- full visibility into who we're actually talking to across the target market -- has zero committed initiatives tracing to it. The TAM coverage map shows exactly how real that gap is: only 25% of the segment's 40 addressable accounts are tracked at all, and within those, Market visibility sits at just 42.5% (17 of 40 required contact cells filled), with Procurement covered at only 2 of 10 tracked accounts and Apex Distribution fully dark. No standing governance rhythm currently exists that would even surface a gap like this on its own -- TAM coverage isn't a recurring agenda item anywhere in the revenue org today.
OBJECTIVE
Establish a standing monthly RevOps governance cadence that includes a Market visibility review, with a named owner assigned to close the true-north statement's pillar-4 gap, by the end of Q2 FY2027.
SCOPE — IN
The recurring governance rhythm for Beacon Analytics' revenue/RevOps function -- weekly pipeline review, monthly planning, quarterly business review -- including who owns each recurring decision and whether market-visibility tracking is a standing agenda item.
SCOPE — OUT
The substance of the FY2027 revenue Hoshin's annual objectives and strategies themselves, which are already committed and owned. This charter governs the cadence and ownership around them, not the objectives.
ROSTER & RACI — 1 accountable
Name | Role | RACI
Priya Anand | RevOps — facilitator | R
Renee Okafor | VP Sales — sponsor | A
Jordan Ellis | Sales Manager — pipeline review owner | R
Sam Cole | Sales Enablement — content/campaign sign-off owner | C
Sales & RevOps team | Attendees | I
READINESS — 3 of 6 ready (50%)
Item | Ready | Note
TAM coverage map's baseline figures (25% list coverage, 42.5% Market visibility) captured as this charter's starting measurement | Y
FY2027 revenue Hoshin's three committed strategies (multi-threading gate, pull-based WIP cap, expansion playbook) confirmed to already have named owners | Y
Sponsor (VP Sales) briefed on why a standing governance cadence is needed beyond this year's Hoshin plan | Y
Weekly pipeline review agenda updated to include a standing Market visibility check | N
Monthly revenue-ops planning cadence booked as a recurring calendar hold across RevOps, Sales, and Sales Enablement | N
A named owner assigned specifically for closing true-north statement's pillar-4 gap | N
NARRATIVE
Three of six readiness items are confirmed: the TAM coverage map's baseline figures are captured, the three committed revenue Hoshin strategies are confirmed to already have named owners, and the sponsor is briefed. Three are honestly still open: the weekly pipeline review agenda doesn't yet include a Market visibility check, no recurring monthly planning cadence is booked, and nobody is specifically named as owner of the pillar-4 gap itself. The roster has exactly one accountable owner, with Priya facilitating and Jordan and Sam holding the two recurring review responsibilities day to day.