## Storyboard
Line 2 paint booth — colour changeover storyboard
Learner: Marcus Webb, Paint Booth Lead · Coach: Priya Nair, Line Supervisor · As of: 2026-05-11
CHALLENGE — the direction, usually six months to three years out
Challenge | By the end of 2027, Line 2's paint booth can switch to any colour in under 10 minutes, so each day's orders are painted in the order they're needed: no holding custom colours for set changeover slots, and no shipment late because of paint.
By | 2027-12-17
Why it matters | The two-slot sequencing rule brought on-time shipments back, but it works by making custom orders wait for a slot. Customers are asking for more custom colours with shorter lead times, and the rule can't stretch that far. Quick changeovers would remove the reason for the rule.
NEXT TARGET CONDITION — how the process should run by a date ahead (usually 1 to 4 weeks), plus a dated outcome
Operating pattern | Every changeover on Line 2's booth runs from materials already staged at the booth, with no walks away from it, and both shifts clean in the same order so nobody waits for walls to dry before the next part of the job.
Outcome metric | Changeover time: 35 minutes or less on 8 of the last 10 changeovers
Target | 35 minutes
Set on / achieve by | 2026-04-24 → 2026-05-15
CURRENT CONDITION — go and see; how the work runs now, and what it produces
Operating pattern | About 3 colour changeovers a shift, each done by the booth operator on duty. The solvent tub and a clean nozzle set are now staged on a cart before the last unit of the old colour, with the nozzle size read from the colour's card on the queue board. The cleaning order differs by shift: first shift cleans the gun, then the booth walls; second shift cleans the walls first and waits for them to dry before cleaning the gun. There's no agreed point at which the booth counts as clean, so each operator judges it.
Outcome | Changeover time, from the last good unit of the old colour to the first good unit of the new one: 34 to 38 minutes over the last 4 changeovers, down from 41 to 52 minutes (middle value 46) in the first week of observation.
Observations
Date | Where | What we saw | Who does the work | Watched or report
2026-04-21 | Line 2 paint booth, first shift | Blue to custom green took 44 minutes. The operator left the booth twice: once for a solvent tub from the stores cage, once for a clean nozzle set. Gun cleaned first, then the booth walls. | Paint booth operator, first shift | Watched
2026-04-22 | Line 2 paint booth, second shift | Grey to red took 52 minutes. Walls cleaned first, then about 8 minutes waiting for them to dry before the gun could be cleaned. Nozzle set fetched part-way through. | Paint booth operator, second shift | Watched
2026-04-23 | Booth changeover log (paper form) | Last 20 logged changeovers ran 38 to 63 minutes; 3 entries have no end time, so the real spread is probably wider. | Paint booth lead, who transcribes the log weekly | Report
2026-05-08 | Line 2 paint booth, both shifts | Cart staged with the right nozzle size both times, and no walks away from the booth. First shift took 35 minutes, gun then walls. Second shift still cleaned the walls first and waited about 6 minutes for them to dry. | Paint booth operators, both shifts | Watched
OBSTACLES PARKING LOT — work on one at a time
Obstacle |  |  |  | In focus | Cleared
Solvent and clean nozzles are fetched from the stores cage in the middle of the changeover. |  |  |  |  | Cleared
Whoever stages the cart can't tell which nozzle size the next colour needs. |  |  |  |  | Cleared
The two shifts clean in a different order; second shift waits for the walls to dry before cleaning the gun. |  |  |  | In focus
No agreed point at which the booth counts as clean.
The nozzle cleaning fixture fits only one of the two spray gun models.
COACHING CYCLE — the coach asks, the learner answers from this board
1. Talk me through the board. Where are you heading, and what have you promised yourself by the date on the target?
2. When did you last watch the work, and what did you see with your own eyes?
3. Your last step: what did you write down that you expected, how did it turn out, and what surprised you?
4. Which obstacle has your attention right now, and why that one first?
5. What will you try next, and what do you predict? Write the prediction before you start.
6. When shall we look at the result together?

## Experiments
Experiment records — one Plan-Do-Check-Act (PDCA) cycle per row
Plan: the step and what you expect, before you start. Do: take the step. Check: what happened, when you go and see. Act: what you learned, which shapes the next step. Never edit the expectation once the result is known.
Step | Observe or change | Obstacle | What we don't know yet | Step we'll take (one change) | What we expect — write before starting | Started | Go and see on | What happened | What we learned
1 | Observe | Solvent and clean nozzles are fetched from the stores cage in the middle of the changeover. | We don't know how much of a changeover goes on walking away from the booth, or what each walk is for. | Go and see 3 first-shift changeovers, timing every walk away from the booth and noting what it was for. Change nothing. | About 10 minutes per changeover spent fetching things, mostly solvent. | 2026-04-27 | 2026-04-29 | Walks took 6, 9 and 14 minutes. The solvent tub was fetched every time and a nozzle set twice. On the 14-minute changeover the stores cage was locked while the key holder was on break. | Fetching is real time, a little less than expected, and the worst case comes from the locked cage, not the distance. If everything is at the booth before the changeover starts, most of the walking should go.
2 | Change | Solvent and clean nozzles are fetched from the stores cage in the middle of the changeover. | We don't know whether staging the materials beforehand removes the walks, or whether something else still sends the operator away. | Before the last unit of the old colour, stage a solvent tub and a clean nozzle set on a cart next to the booth. First shift only. | No walks away from the booth, and changeovers down by about 8 minutes, to around 38 minutes. | 2026-04-30 | 2026-05-04 | 3 changeovers: 37, 35 and 41 minutes. No walks on the first two. On the third the cart held the wrong nozzle size, so the operator went to the cage for the right one. | Staging removes the walking when the cart is right, and saves a little more time than expected. Whoever stages the cart can't tell which nozzle size the next colour needs: a new obstacle, added to the parking lot.
3 | Change | Whoever stages the cart can't tell which nozzle size the next colour needs. | We don't know whether having the nozzle size on the colour's queue card is enough for the cart to be right every time. | Write the nozzle size on each colour's card on the queue board, so whoever stages the cart takes the size from the card. | Right nozzle on the cart for every changeover this week, no walks, and changeovers around 36 minutes. | 2026-05-05 | 2026-05-07 | 3 changeovers: 36, 34 and 38 minutes, right nozzle every time and no walks. The 38-minute one was on second shift, where the walls were cleaned first and the operator waited for them to dry. | The card works. The spread that's left seems to come from the cleaning order, which differs by shift. That's the next obstacle to work on, and we don't yet know why the orders differ.
4 | Observe | The two shifts clean in a different order; second shift waits for the walls to dry before cleaning the gun. | We don't know why second shift cleans the walls first, or how long the drying wait really is. | Go and see 2 second-shift changeovers, writing down the cleaning steps in the order they happen and timing the wait for the walls to dry. Ask the operator what that order protects against. | The walls-first order is a habit from the solvent used before, and the drying wait is 6 to 8 minutes each time. | 2026-05-11 | 2026-05-12 | Waiting to go and see

## Metric
Changeover time (minutes)
Record each value on the day you measure it. Target is the next target condition's number.
Date | Value | Target
2026-04-21 | 44 | 35
2026-04-22 | 52 | 35
2026-04-23 | 46 | 35
2026-04-27 | 46 | 35
2026-04-28 | 49 | 35
2026-04-29 | 41 | 35
2026-04-30 | 37 | 35
2026-05-01 | 35 | 35
2026-05-04 | 41 | 35
2026-05-05 | 36 | 35
2026-05-06 | 34 | 35
2026-05-07 | 38 | 35
2026-05-08 | 35 | 35