## Performance grid
Inside sales — weekly performance grid
Inside sales, Northern region · Priya Raman, Inside Sales Lead · 2026-09-16 · One square per week · Team: Dan Whitfield, Sales Development, Marta Kowal, Solutions, Owen Reid, Sales Operations
THE GRID
Category | Measure | Goal | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37
Customer | New enquiries answered same day | ≥ 95% | 97% | 91% | 96% | 89% | 98%
Quality | Proposals out within two days of qualification | ≥ 90% | 92% | 78% | 81% | 84% | 93%
Delivery | Deals slipping their committed close date | ≤ 2 | 1 | 2 | 5 | 2 | 1
People | Team capacity | Judgement
Red missed the rule. Green met it. Blue means the number is not in yet — an unmeasured period is not a good one.
THE RULES — AGREED BEFORE THE PERIOD STARTS, SO COLOUR IS NEVER ARGUED AFTERWARDS
New enquiries answered same day | Red if fewer than 95% of enquiries received a substantive reply the same working day. · Source: Customer relationship management (CRM) system, first-response report · Owner: Dan Whitfield
Proposals out within two days of qualification | Red if fewer than 90% of qualified opportunities had a proposal issued within two working days. · Source: CRM, qualification-to-proposal timestamp · Owner: Marta Kowal
Deals slipping their committed close date | Red if more than two deals moved their committed close date this week. · Source: CRM, close-date change history · Owner: Owen Reid
Team capacity | Red if anyone worked a weekend, or if cover was unfilled for a whole day. · Source: Team, at the huddle · Owner: Priya Raman
EVERY RED, AND WHY
Measure | Period | Reason (what happened, never who)
New enquiries answered same day | Wk 34 | Two people out on the Tuesday, nobody picked up the shared inbox |  |  |  |  | Shared inbox uncovered
New enquiries answered same day | Wk 36 | Shared inbox again — Thursday, both cover names were in the same workshop |  |  |  |  | Shared inbox uncovered
Proposals out within two days of qualification | Wk 34 | Waiting on pricing sign-off for three deals over the discount threshold |  |  |  |  | Pricing approval wait
Proposals out within two days of qualification | Wk 35 | Pricing sign-off again — approver on leave, no named deputy |  |  |  |  | Pricing approval wait
Proposals out within two days of qualification | Wk 36 | Pricing sign-off, two deals held to Monday |  |  |  |  | Pricing approval wait
Deals slipping their committed close date | Wk 35 | Not recorded — this square can teach nobody anything now.
Team capacity | Wk 34 | Two out sick, no cover arranged for the inbox |  |  |  |  | Shared inbox uncovered
WHAT IS BEING DONE
Linked red | Countermeasure | Type | Owner | Expected outcome | Due | Closed | Evidence
New enquiries answered same day — Wk 34 | Named cover for the shared inbox published each Friday for the week ahead, with a second name when the first is in a workshop. | Permanent | Dan Whitfield | Same-day replies back above 95% and holding there for three straight weeks. | 2026-09-11 | Open
Proposals out within two days of qualification — Wk 34 | Deals over the discount threshold routed to a standing deputy approver when the primary approver is away. | Containment | Marta Kowal | No proposal waits on an absent approver again; two-day issue rate back above 90% next week. | 2026-09-04 | 2026-09-04 | Wk 37 proposals all issued inside two days; no deal waited on an absent approver.
Proposals out within two days of qualification — Wk 36 | Raise the discount threshold so routine deals do not need sign-off at all — proposal drafted for the regional director. | Permanent | Priya Raman | Roughly four in five deals stop needing sign-off at all, so the approval wait cannot cause a red. | 2026-09-30 | Open
Team capacity — Wk 34 | Sickness cover agreed with the neighbouring team, both ways. | Containment | Priya Raman | The inbox stays answered through the next absence without anyone working late. | 2026-09-09 | 2026-09-08 | Cover used once in Wk 36; inbox stayed answered.
WHICH CAUSES KEEP COMING BACK
Reason | Reds | % of reds | Cumulative %
Pricing approval wait | 3 | 42.9% | 42.9%
Shared inbox uncovered | 3 | 42.9% | 85.8%
Not recorded | 1 | 14.3% | 100%
DISCIPLINE CHECKS
Squares | 20 — 7 red, 12 green, 1 not measured
Reds with no reason | 1
Reds with nothing being done | 3
Countermeasures open | 2
Countermeasures past their date | 1
Repeat misses | None.
WHAT THE GRID SAYS
Twenty squares, seven of them red — and two causes account for six of those seven. That is the grid doing its job: it has turned a scattered week-by-week grumble into two problems worth solving. Pricing approval held up three proposals across three separate weeks; the containment, a standing deputy approver, held in week 37, and the permanent fix — raising the discount threshold so routine deals never need sign-off at all — is open and not yet due. The other three reds all trace to an uncovered shared inbox, and they show up on two different measures, which is the clue that it is a staffing rule rather than a sales problem. That countermeasure is past its date and needs closing or re-dating at the next huddle. Three reds still have nothing being done about them, and one of those — deals slipping their close date in week 35 — was never given a reason at all, so it is the one square nobody can learn anything from now. Week 37 capacity has not been marked yet, which is blue rather than green: an unmeasured period is not a good one.