## Scoping canvas
Scoping canvas — Line 2 paint booth changeover event
Priya Nair, Line Supervisor · 2026-02-20 · Team: Marcus Webb, Paint Booth Lead, Dana Ruiz, Scheduling · Sponsor: Oksana Petrova, Plant Manager
PROBLEM / OPPORTUNITY
• The A3 on Line 2's on-time shipment rate (2026-02-03) traced the root cause to no standard rule for sequencing small-batch orders into the paint schedule — its two committed countermeasures (a fixed changeover-slot rule, a visual queue board) close the immediate gap but don't touch the underlying changeover time itself.
• Even with the new sequencing rule, a full changeover still costs the same ~45 minutes it always has — a kaizen event on the changeover procedure itself is the next lever once the sequencing fix has had time to prove out.
GOAL STATEMENT
• Cut single changeover time on the Line 2 paint booth from ~45 minutes to under 25 minutes within one quarter of the event, without adding headcount.
IN SCOPE
• The physical changeover procedure itself — setup, color-switch, cleanup steps — for the Line 2 paint booth only.
• Tooling and fixture changes that fit within the existing booth footprint.
OUT OF SCOPE
• The small-batch sequencing rule itself — already decided and rolling out via the A3's countermeasures, not re-opened here.
• Line 1's paint booth — explicitly deferred in the A3's follow-up actions until Line 2's results are in.
• Capital equipment purchases — this event works within existing tooling only.
TEAM & STAKEHOLDERS
• Marcus Webb (paint booth lead) runs the changeover time studies.
• Dana Ruiz (scheduling) confirms any procedure change doesn't conflict with the new sequencing rule.
• Oksana Petrova (plant manager) sponsors and clears floor time for the event.
TIMELINE
• Week 1: baseline time study on 5 real changeovers.
• Week 2: kaizen event — a single 3-day session to redesign the procedure.
• Weeks 3-4: trial the new procedure, adjust based on real changeovers.
• End of quarter: confirm sustained time against the 25-minute target.
ASSUMPTIONS & CONSTRAINTS
• Assumes the A3's sequencing rule is holding by the time this event starts — if changeover frequency is still unpredictable, the time-study baseline won't be representative.
• No budget assumed for new tooling; any fixture changes have to use materials already on hand or trivially sourced.
NARRATIVE
This event picks up directly where the A3 left off: the sequencing rule stops changeovers from happening at the wrong time, but it doesn't make any single changeover faster. Scoped tightly to the physical changeover procedure on Line 2 only — Line 1 and any capital spend are explicitly deferred — with a short baseline-then-event-then-trial timeline that fits inside one quarter, matching the A3's own effect-confirmation window.