## Sustainment audit
60-day sustainment check — onboarding ticket resolution event
Auditing: Reduce onboarding support ticket resolution time (Sep 2026 kaizen event) · Auditor: Priya Nair · 2026-11-16 (60 days since event)
ORIGINAL OBJECTIVE
Cut median resolution time for first-two-weeks onboarding tickets from 6.2 hours to under 3 hours, without increasing the reopened-ticket rate.
SUSTAINMENT CHECKS — 4 of 6 holding (67%)
Practice | Holding | Note
New triage macro for setup/SSO tickets still in active use | Y
Median resolution time still tracked weekly on the support dashboard | Y
Original event owner (Marcus Lee) still assigned to the metric | Y
Updated setup docs still linked from the initial-response macro | N
Reopened-ticket rate still reviewed alongside resolution time | N
Support team still following the event's triage routing change | Y
NARRATIVE
Four of six practices are still holding two months after the event — the new triage macro, weekly dashboard tracking, and the routing change have stuck, and Marcus Lee is still the named owner. Two are at risk: the updated setup docs are no longer linked from the macro, and the reopened-ticket rate has quietly dropped out of the weekly review. Both are worth a quick fix before they fully lapse.