## VOC collection plan
H1 2026 VOC collection plan
Dana Whitfield, Product Lead · 2026-01-15 · Team: Marcus Lee, Support, Priya Nair, Customer Success · Sponsor: Alex Romero, VP Product
SCOPE
Covers new and existing customers across all segments for the first half of 2026 — the standing collection activities that keep the VOC evidence log fed, not a one-time research push.
COVERAGE — 4 goals · 3 activities
Gap — no collection activity yet: Understand why enterprise deals stall in negotiation
GOALS
• Understand why onboarding friction happens
• Understand why pricing confusion happens
• Understand what's driving early support ticket spikes
• Understand why enterprise deals stall in negotiation
COLLECTION ACTIVITIES
Method | Linked goal | Owner | Cadence | Evidence flow
Customer interviews (customer interview guide) | Understand why onboarding friction happens | Dana Whitfield | Monthly — 3 to 5 customers, 30 to 60 days into their contract | Interviewer logs quotes into the VOC evidence log within 48 hours of each interview.
Support ticket tagging | Understand why pricing confusion happens | Marcus Lee | Ongoing — tagged as tickets come in, reviewed weekly | Support tags tickets with a 'pricing confusion' label; Marcus pulls tagged tickets into the evidence log every Friday.
Gemba sessions (gemba interview protocol) | Understand what's driving early support ticket spikes | Marcus Lee | Quarterly — one full support shift observed | Observations logged the same day, source type 'gemba'.
NARRATIVE
Three of the four goals have a real, standing collection activity behind them — onboarding friction and pricing confusion both have monthly or ongoing sources already in motion, and the support gemba session adds a direct-observation channel quarterly. The fourth goal, enterprise deals stalling in negotiation, has no activity yet — that's a real gap, not an oversight, and the natural next step given the win-loss interview guide already exists for exactly this kind of question.