## WIP aging
IT service request queue — WIP aging
Sam Torres, Service Desk Lead · As of 2026-03-01 · Team: Nina Petrov, Support · Sponsor: Alex Romero, IT Director
SCOPE
Scope covers every open service request as of 2026-03-01, across triage, in-progress, and review — excludes closed requests, which are a separate reporting view.
OPEN ITEMS
Item | Stage | Entered | Age (days)
REQ-101 | Triage | 2026-02-27 | 2
REQ-102 | Triage | 2026-02-26 | 3
REQ-103 | Triage | 2026-01-15 | 45
REQ-104 | In progress | 2026-02-20 | 9
REQ-105 | In progress | 2026-02-15 | 14
REQ-106 | Review | 2026-02-28 | 1
STAGE AVERAGES
Stage | Items | Average age (days)
Triage | 3 | 16.7
In progress | 2 | 11.5
Review | 1 | 1
OVERALL SUMMARY
6 open items, average age 12.3 days
(2 + 3 + 45 + 9 + 14 + 1) / 6 = 12.3 days
Oldest item: REQ-103 (Triage) at 45 days
Stalled — REQ-103 (Triage): 45 days is at least 2x this stage's average of 16.7 days — this item is stalled relative to its peers.
NARRATIVE
REQ-103 is the one stalled item, sitting in triage for 45 days against that stage's 16.7-day average — more than double, and the oldest item in the whole queue. The observation notes point to an unanswered vendor follow-up as the specific blocker, not a triage-process problem generally, since the other two triage items are both under a week old. Overall queue average age is 12.3 days across 6 open items.
COUNTERMEASURES
Description |  | Linked finding | Impact | Effort | Owner | Due
Escalate the outstanding vendor follow-up on REQ-103 directly rather than waiting on the vendor's own SLA, since the ticket has already sat unanswered for 45 days. |  | REQ-103 — stalled at 45 days, 2.7x the triage stage average | high | low | Sam Torres — 2026-03-08
Add a standing follow-up reminder for any triage ticket blocked on a third party for more than 10 days, so a REQ-103 situation surfaces automatically instead of relying on someone noticing. |  | REQ-103 — 45 days with no follow-up recorded since the initial ticket | medium | low | Nina Petrov — 2026-03-15